## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2221-swen-261-06-maple-leafs
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a product user, I want to be able to login to a specified user account so I can do user specific stuff | GIVEN I try to login WHEN the username matches THEN I will be logged in
GIVEN I try to login WHEN the username doesn't match THEN the webpage will say the account doesn't exist
As a buyer I want to look up specific jerseys so I can find the jersey I want to buy | GIVEN I am at the search bar WHEN I enter a name THEN the website will show every jersey that has that name in it
GIVEN I am at the search bar WHEN nothing is entered THEN the website will show every jersey in the inventory
GIVEN I am at the search bar WHEN I enter a name that doesn't relate to any jersey THEN the website will display that no products were found
As an Admin, I want to see the specified information of a jersey, so I understand the product that I am interested in | GIVEN I am at the search bar WHEN I click on a jersey THEN I will be sent to the individual jersey's page (include player name, player number, cost, size dropdown menu, home/away, ID number), with buttons to go back, update, and delete
GIVEN I am viewing a jersey's page WHEN I click the back button THEN I will go back to the search bar
GIVEN I am viewing a jersey's page WHEN I want a jersey in a specific size THEN I will be able to select that size
As a buyer, I want to see the specified information of a jersey, so I understand the product that I am interested in | GIVEN I am at the search bar WHEN I click on a jersey THEN I will be sent to the individual jersey's page (include player name, player number, cost, size dropdown menu, home/away, ID number), with buttons to go back and buy
GIVEN I am viewing a jersey's page WHEN I click the back button THEN I will go back to the search bar
GIVEN I am viewing a jersey's page WHEN I want a jersey in a specific size THEN I will be able to select that size
As an Admin I want to remove jerseys so that customers won't see jerseys that are no longer available. | GIVEN The Admin is viewing a specific jersey WHEN the "delete jersey" button is clicked THEN a confirmation alert is shown
GIVEN the Admin clicked the "delete" jersey button WHEN confirm is clicked in the confirmation alert THEN the page will display a Jersey Not Found page
GIVEN a jersey has been deleted WHEN the admin goes back to the browsing products page THEN the deleted jersey should not be displayed
As an Admin I want to add jerseys so that I can show my customers what is available to buy. | GIVEN The Admin is viewing the available jerseys WHEN the "create jersey" button is clicked THEN a new page is displayed with fields to input a new jersey
GIVEN the Admin has the fields filled out and clicks the "add jersey" button WHEN there is no existing jersey with the same content THEN the new jersey should be created
GIVEN a jersey has been created WHEN the admin goes back to the browsing products page THEN the created jersey should be displayed